## Sheet1
USER_INPUT
Country | Project Code | Technology | Scope | Project Volume | Project Duration
Qatar | Project#1 | SRAN | New | 789 | 10
UAE | Project#1 | MW | Swap | 790 | 12
UAE | Project#1 | 5G | New | 999 | 5
UAE | Project#1 | CW | Exp | 555 | 10
MAIN_TABLE
Market Unit | Country | Risk | Project Code | Technology | Scope | Project Volume | Project Duration
NA | Qatar | Low Risk | Project#1 | SRAN | New | 789 | 10
ME | UAE | Low Risk | Project#1 | 5G | New | 999 | 12
ME | UAE | Low Risk | Project#1 | MW | Swap | 790 | 5
ME | UAE | Low Risk | Project#1 | CW | Exp | 555 | 10
TEAM_DIMENSION
SRAN
Milestone/teams | P1 | P2 | P3 | P4 | P5 | P6 | P7 | P8 | P9 | P10 | P11 | P12
TSSR PIP | 59.175 | 169.2833 | 220.2167 | 220.2167 | 220.2167 | 169.2833 | A7 | A8 | A9 | A10
RO PIP | 19.725 | 39.45 | 59.175 | 110.1083 | 110.1083 | 110.1083 | 110.1083 | 110.1083 | 110.1083 | 110.1083
TSSR Teams | 1.8492 | 5.2901 | 4.5878 | 4.5878 | 4.5878 | 3.5267 | C7 | C8 | C9 | C10
SRAN Teams | 4.9313 | 9.8625 | 14.7938 | 18.3514 | 18.3514 | 18.3514 | 18.3514 | 18.3514 | 18.3514 | 18.3514
Supervisors | 1.2328 | 2.4656 | 3.6984 | 4.5878 | 4.5878 | 4.5878 | 4.5878 | 4.5878 | 4.5878 | 4.5878
FDM | 1 | 1 | 1 | 1.147 | 1.147 | 1.147 | 1.147 | 1.147 | 1.147 | 1.147
RIC Engineer | 1 | 1 | 1 | 1.1011 | 1.1011 | 1.1011 | 1.1011 | 1.1011 | 1.1011 | 1.1011
5G
Milestone/teams | P1 | P2 | P3 | P4 | P5 | P6 | P7 | P8 | P9 | P10 | P11 | P12
TSSR PIP | 62.4375 | 170.2031 | 215.5312 | 215.5312 | 215.5312 | 170.2031 | A7 | A8 | A9 | A10 | A11 | A12
RO PIP | 20.8125 | 41.625 | 62.4375 | 107.7656 | 107.7656 | 107.7656 | 107.7656 | 107.7656 | 107.7656 | 107.7656 | 107.7656 | 62.4375
TSSR Teams | 1.9512 | 5.3188 | 4.4902 | 4.4902 | 4.4902 | 3.5459 | C7 | C8 | C9 | C10 | C11 | C12
5G Teams | 3.9023 | 7.8047 | 11.707 | 13.4707 | 13.4707 | 13.4707 | 13.4707 | 13.4707 | 13.4707 | 13.4707 | 13.4707 | 7.8047
Supervisors | 1 | 1.9512 | 2.9268 | 3.3677 | 3.3677 | 3.3677 | 3.3677 | 3.3677 | 3.3677 | 3.3677 | 3.3677 | 1.9512
FDM | bar: P1 to P12
RIC Engineer | 1 | 1 | 1 | 1.0777 | 1.0777 | 1.0777 | 1.0777 | 1.0777 | 1.0777 | 1.0777 | 1.0777 | 1
MW
Milestone/teams | P1 | P2 | P3 | P4 | P5 | P6 | P7 | P8 | P9 | P10 | P11 | P12
TSSR PIP | P1: 118.5; P2: 666.5; P3: 1096; P4: 1096; P5: 1096
RO PIP | P1: 39.5; P2: 79; P3: 118.5; P4: 548; P5: 548
MW Teams | P1: 3.7031; P2: 20.8281; P3: 22.8333; P4: 22.8333; P5: 22.8333
5G Teams | P1: 9.875; P2: 19.75; P3: 29.625; P4: 91.3333; P5: 91.3333
Supervisors | P1: 2.4688; P2: 4.9375; P3: 7.4062; P4: 22.8333; P5: 22.8333
FDM | P1: 1; P2: 1.2344; P3: 1.8516; P4: 5.7083; P5: 5.7083
RIC Engineer | P1: 1; P2: 1; P3: 1.185; P4: 5.48; P5: 5.48
CW
Milestone/teams | P1 | P2 | P3 | P4 | P5 | P6 | P7 | P8 | P9 | P10 | P11 | P12
TSSR PIP | 41.625 | 118.5833 | 153.9167 | 153.9167 | 153.9167 | 118.5833 | A7 | A8 | A9 | A10
RO PIP | 13.875 | 27.75 | 41.625 | 76.9583 | 76.9583 | 76.9583 | 76.9583 | 76.9583 | 76.9583 | 76.9583
CW Teams | 1.3008 | 3.7057 | 3.2066 | 3.2066 | 3.2066 | 2.4705 | C7 | C8 | C9 | C10
5G Teams | 2.6016 | 5.2031 | 7.8047 | 9.6198 | 9.6198 | 9.6198 | 9.6198 | 9.6198 | 9.6198 | 9.6198
Supervisors | 1 | 1.3008 | 1.9512 | 2.4049 | 2.4049 | 2.4049 | 2.4049 | 2.4049 | 2.4049 | 2.4049
FDM | bar: P1 to P10
RIC Engineer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
COMMON TEAM
Milestone/teams | P1 | P2 | P3 | P4 | P5 | P6 | P7 | P8 | P9 | P10 | P11 | P12
Rollout Manager | 1.3333 | 1.4115 | 1.6172 | 2.9518 | 2.9518 | 2.9518 | 2.9518 | 2.9518 | 2.9518 | 2.9518 | 2.9518 | 1.4115
Project Manager | bar: P1 to P12
QHSE Auditor | 1 | 1 | 1.4087 | 4.2142 | 4.2142 | 4.2142 | 4.2142 | 4.2142 | 4.2142 | 4.2142 | 4.2142 | 1.4087
Project Coordinator | 1 | 1.2522 | 1.8782 | 5.6189 | 5.6189 | 5.6189 | 5.6189 | 5.6189 | 5.6189 | 5.6189 | 5.6189 | 1.8782
Site Engineering | 1 | 1.2522 | 1.8782 | 5.6189 | 5.6189 | 5.6189 | 5.6189 | 5.6189 | 5.6189 | 5.6189 | 5.6189 | 1.8782
Materials Manager | 1 | 1.2522 | 1.8782 | 5.6189 | 5.6189 | 5.6189 | 5.6189 | 5.6189 | 5.6189 | 5.6189 | 5.6189 | 1.8782
Acceptance Manager | bar: P1 to P12
Acceptance supervisor | 1.2522 | 2.5043 | 3.7565 | 11.2378 | 11.2378 | 11.2378 | 11.2378 | 11.2378 | 11.2378 | 11.2378 | 11.2378 | 3.7565
SAQ coordinator | 1 | 1.2522 | 1.8782 | 5.6189 | 5.6189 | 5.6189 | 5.6189 | 5.6189 | 5.6189 | 5.6189 | 5.6189 | 1.8782

## Sheet2
SRAN | [9 empty] | Common for SRAN+5G+MW+CW
TSSR PIP | RO PIP | TSSR Teams | SRAN Teams | 5G Teams | MW Teams | CW Teams | Supervisors | FDM | RIC Engineer | ROM | PM | QHSE Auditor | Project Coordinator | Site Engineering | Materials Manager | Acceptance Manager | Acceptance supervisor | SAQ coordinator
59.175 | 19.725 | 1.8492 | 4.9313 |  |  |  | 1.2328 | 1 | 1 | 1.3333 | 1 | 1 | 1 | 1 | 1 | 1 | 1.2522 | 1 | P1
169.2833 | 39.45 | 5.2901 | 9.8625 |  |  |  | 2.4656 | 1 | 1 | 1.4115 | 1 | 1 | 1.2522 | 1.2522 | 1.2522 | 1 | 2.5043 | 1.2522 | P2
220.2167 | 59.175 | 4.5878 | 14.7938 |  |  |  | 3.6984 | 1 | 1 | 1.6172 | 1 | 1.4087 | 1.8782 | 1.8782 | 1.8782 | 1 | 3.7565 | 1.8782 | P3
220.2167 | 110.1083 | 4.5878 | 18.3514 |  |  |  | 4.5878 | 1.147 | 1.1011 | 2.9518 | 1 | 4.2142 | 5.6189 | 5.6189 | 5.6189 | 1 | 11.2378 | 5.6189 | P4
220.2167 | 110.1083 | 4.5878 | 18.3514 |  |  |  | 4.5878 | 1.147 | 1.1011 | 2.9518 | 1 | 4.2142 | 5.6189 | 5.6189 | 5.6189 | 1 | 11.2378 | 5.6189 | P5
169.2833 | 110.1083 | 3.5267 | 18.3514 |  |  |  | 4.5878 | 1.147 | 1.1011 | 2.9518 | 1 | 4.2142 | 5.6189 | 5.6189 | 5.6189 | 1 | 11.2378 | 5.6189 | P6
A7 | 110.1083 | C7 | 18.3514 |  |  |  | 4.5878 | 1.147 | 1.1011 | 2.9518 | 1 | 4.2142 | 5.6189 | 5.6189 | 5.6189 | 1 | 11.2378 | 5.6189 | P7
A8 | 110.1083 | C8 | 18.3514 |  |  |  | 4.5878 | 1.147 | 1.1011 | 2.9518 | 1 | 4.2142 | 5.6189 | 5.6189 | 5.6189 | 1 | 11.2378 | 5.6189 | P8
A9 | 110.1083 | C9 | 18.3514 |  |  |  | 4.5878 | 1.147 | 1.1011 | 2.9518 | 1 | 4.2142 | 5.6189 | 5.6189 | 5.6189 | 1 | 11.2378 | 5.6189 | P9
A10 | 110.1083 | C10 | 18.3514 |  |  |  | 4.5878 | 1.147 | 1.1011 | 2.9518 | 1 | 4.2142 | 5.6189 | 5.6189 | 5.6189 | 1 | 11.2378 | 5.6189 | P10
A11 | 110.1083 | C11 | 18.3514 |  |  |  | 4.5878 | 1.147 | 1.1011 | 2.9518 | 1 | 4.2142 | 5.6189 | 5.6189 | 5.6189 | 1 | 11.2378 | 5.6189 | P11
A12 | 59.175 | C12 | 9.8625 |  |  |  | 2.4656 | 1 | 1 | 1.4115 | 1 | 1.4087 | 1.8782 | 1.8782 | 1.8782 | 1 | 3.7565 | 1.8782 | P12
5G
TSSR PIP | RO PIP | TSSR Teams | SRAN Teams | 5G Teams | MW Teams | CW Teams | Supervisors | FDM | RIC Engineer
62.4375 | 20.8125 | 1.9512 |  | 3.9023 |  |  | 1 | 1 | 1 | P1
170.2031 | 41.625 | 5.3188 |  | 7.8047 |  |  | 1.9512 | 1 | 1 | P2
215.5312 | 62.4375 | 4.4902 |  | 11.707 |  |  | 2.9268 | 1 | 1 | P3
215.5312 | 107.7656 | 4.4902 |  | 13.4707 |  |  | 3.3677 | 1 | 1.0777 | P4
215.5312 | 107.7656 | 4.4902 |  | 13.4707 |  |  | 3.3677 | 1 | 1.0777 | P5
170.2031 | 107.7656 | 3.5459 |  | 13.4707 |  |  | 3.3677 | 1 | 1.0777 | P6
A7 | 107.7656 | C7 |  | 13.4707 |  |  | 3.3677 | 1 | 1.0777 | P7
A8 | 107.7656 | C8 |  | 13.4707 |  |  | 3.3677 | 1 | 1.0777 | P8
A9 | 107.7656 | C9 |  | 13.4707 |  |  | 3.3677 | 1 | 1.0777 | P9
A10 | 107.7656 | C10 |  | 13.4707 |  |  | 3.3677 | 1 | 1.0777 | P10
A11 | 107.7656 | C11 |  | 13.4707 |  |  | 3.3677 | 1 | 1.0777 | P11
A12 | 62.4375 | C12 |  | 7.8047 |  |  | 1.9512 | 1 | 1 | P12
MW
TSSR PIP | RO PIP | TSSR Teams | SRAN Teams | 5G Teams | MW Teams | CW Teams | Supervisors | FDM | RIC Engineer
118.5 | 39.5 | 3.7031 |  |  | 9.875 |  | 2.4688 | 1 | 1 | P1
666.5 | 79 | 20.8281 |  |  | 19.75 |  | 4.9375 | 1.2344 | 1 | P2
1096 | 118.5 | 22.8333 |  |  | 29.625 |  | 7.4062 | 1.8516 | 1.185 | P3
1096 | 548 | 22.8333 |  |  | 91.3333 |  | 22.8333 | 5.7083 | 5.48 | P4
1096 | 548 | 22.8333 |  |  | 91.3333 |  | 22.8333 | 5.7083 | 5.48 | P5
666.5 | 548 | 13.8854 |  |  | 91.3333 |  | 22.8333 | 5.7083 | 5.48 | P6
A7 | 548 | C7 |  |  | 91.3333 |  | 22.8333 | 5.7083 | 5.48 | P7
A8 | 548 | C8 |  |  | 91.3333 |  | 22.8333 | 5.7083 | 5.48 | P8
A9 | 548 | C9 |  |  | 91.3333 |  | 22.8333 | 5.7083 | 5.48 | P9
A10 | 548 | C10 |  |  | 91.3333 |  | 22.8333 | 5.7083 | 5.48 | P10
A11 | 548 | C11 |  |  | 91.3333 |  | 22.8333 | 5.7083 | 5.48 | P11
A12 | 118.5 | C12 |  |  | 19.75 |  | 4.9375 | 1.2344 | 1.185 | P12
CW
TSSR PIP | RO PIP | TSSR Teams | SRAN Teams | 5G Teams | MW Teams | CW Teams | Supervisors | FDM | RIC Engineer
41.625 | 13.875 | 1.3008 |  |  |  | 2.6016 | 1 | 1 | 0 | P1
118.5833 | 27.75 | 3.7057 |  |  |  | 5.2031 | 1.3008 | 1 | 0 | P2
153.9167 | 41.625 | 3.2066 |  |  |  | 7.8047 | 1.9512 | 1 | 0 | P3
153.9167 | 76.9583 | 3.2066 |  |  |  | 9.6198 | 2.4049 | 1 | 0 | P4
153.9167 | 76.9583 | 3.2066 |  |  |  | 9.6198 | 2.4049 | 1 | 0 | P5
118.5833 | 76.9583 | 2.4705 |  |  |  | 9.6198 | 2.4049 | 1 | 0 | P6
A7 | 76.9583 | C7 |  |  |  | 9.6198 | 2.4049 | 1 | 0 | P7
A8 | 76.9583 | C8 |  |  |  | 9.6198 | 2.4049 | 1 | 0 | P8
A9 | 76.9583 | C9 |  |  |  | 9.6198 | 2.4049 | 1 | 0 | P9
A10 | 76.9583 | C10 |  |  |  | 9.6198 | 2.4049 | 1 | 0 | P10
A11 | 76.9583 | C11 |  |  |  | 9.6198 | 2.4049 | 1 | 0 | P11
A12 | 41.625 | C12 |  |  |  | 5.2031 | 1.3008 | 1 | 0 | P12

## Sheet3
1 |  |  | Duration | 0.5 | 4 | 3 | 5 | 3 | 3 | 4 | 3 | 3 | 4 | 10 | 3
2 | Bussiness as usual | Low Risk | Productivity/Month | 48 | 6 | 8 | 4.8 | 8 | 8 | 6 | 8 | 8 | 6 | 2.4 | 8
3 |  | Medium Risk | Productivity/Month | 38.4 | 4.8 | 6.4 | 3.84 | 6.4 | 6.4 | 4.8 | 6.4 | 6.4 | 4.8 | 1.92 | 6.4
4 |  | High Risk | Productivity/Month | 32 | 4 | 5.3333 | 3.2 | 5.3333 | 5.3333 | 4 | 5.3333 | 5.3333 | 4 | 1.6 | 5.3333
5 |  | Very High risk | Productivity/Month | 24 | 3 | 4 | 2.4 | 4 | 4 | 3 | 4 | 4 | 3 | 1.2 | 4
6 | Start Up | Low Risk | Productivity/Month | 32 | 4 | 5.3333 | 3.2 | 5.3333 | 5.3333 | 4 | 5.3333 | 5.3333 | 4 | 1.6 | 5.3333
7 |  | Medium Risk | Productivity/Month | 25.6 | 3.2 | 4.2667 | 2.56 | 4.2667 | 4.2667 | 3.2 | 4.2667 | 4.2667 | 3.2 | 1.28 | 4.2667
8 |  | High Risk | Productivity/Month | 21.3333 | 2.6667 | 3.5556 | 2.1333 | 3.5556 | 3.5556 | 2.6667 | 3.5556 | 3.5556 | 2.6667 | 1.0667 | 3.5556
9 |  | Very High risk | Productivity/Month | 16 | 2 | 2.6667 | 1.6 | 2.6667 | 2.6667 | 2 | 2.6667 | 2.6667 | 2 | 0.8 | 2.6667
|  |  |  | L | M | N | O | P | Q | R | S | T | U | V | W
|  |  |  | TSSR | SRAN | SRAN | SRAN | 5G | 5G | 5G | MW | MW | MW | CW | CW
|  |  |  | All | NEW | Expansion | Swap | NEW | Expansion | Swap | NEW | Expansion | Swap | New | Expansion

## Sheet4
Country | Risk | Region | Market Unit | Project Code | Technology | Scope
UAE | Low Risk | MEA | ME | Project#1 | SRAN | New
Qatar | Low Risk | MEA | NA | Project#2 | 5G | Swap
Oman | Low Risk | MEA | Saudi | Project#3 | MW | Exp
Bahrain | Low Risk | MEA | CEWA | Project#4 | CW
Rwanda | Low Risk | MEA | SAV
Jordan | Low Risk
Moroco | Low Risk
Saudi Arabia | Low Risk
Maurtitus | Low Risk
Kuwait | Low Risk
Senegal | Low Risk
Egypt | Low Risk
Namibia | Low Risk
Tunisia | Low Risk
Alegria | Low Risk
Madagascar | Low Risk
Cyshell | Low Risk
Comoros | Low Risk
Cape Verdi | Low Risk
Kenya | Medium Risk
Ghana | Medium Risk
Zambia | Medium Risk
Uganda | Medium Risk
Lebanon | Medium Risk
Tanzania | Medium Risk
Ethiopia | Medium Risk
Cameron | Medium Risk
Pakistan | Medium Risk
Muaritania | Medium Risk
Eriteria | Medium Risk
Dijibouti | Medium Risk
Congo | Medium Risk
Gabon | Medium Risk
Benin | Medium Risk
Equatorial Guniea | Medium Risk
Togo | Medium Risk
Cote D'ivoir | Medium Risk
Liberia | Medium Risk
Sierraleone | Medium Risk
Guniea | Medium Risk
Guniea Bissau | Medium Risk
Gambia | Medium Risk
Malawi | Medium Risk
Mozambique | Medium Risk
Zimbabwe | Medium Risk
Botswana | Medium Risk
Eswatini | Medium Risk
Lesoto | Medium Risk
South Africa | Medium Risk
Angola | Medium Risk
Burundi | Medium Risk
Western Sahara | Medium Risk
Nigeria | High Risk
Libya | High Risk
South Sudan | High Risk
Somalia | High Risk
Central Africa | High Risk
Mali | High Risk
Burkina Faso | High Risk
Congo DRC | High Risk
Chad | High Risk
Niger | High Risk
Syria | Very High
Yamen | Very High
Sudan | Very High
Iraq | Very High
Iran | Very High
Palestine | Very High

## workout-formula
Remark-1 | Remark-2 | Scope | Risk Catogry | Ref | Milestone/teams | P1 | P2 | P3 | P4 | P5 | P6 | P7 | P8 | P9 | P10 | P11 | P12
Number of A =Duration/2 |  |  |  | A | TSSR PIP | B1+B2 | B3+B4 | B5+B6 | B7+B8 | B9+B10 | B11+B12 | A7 | A8 | A9 | A10 | A11 | A12
Number of B = Duarion |  |  |  | B | RO PIP | (Volume/Duration)*0.25 | (Volume/Duration)*0.5 | (Volume/Duration)*0.75 | (Volume-B1-B2-B3-BN)(Duration-4) | (Volume-B1-B2-B3-BN)(Duration-4) | (Volume-B1-B2-B3-BN)(Duration-4) | (Volume-B1-B2-B3-BN)(Duration-4) | (Volume-B1-B2-B3-BN)(Duration-4) | (Volume-B1-B2-B3-BN)(Duration-4) | (Volume-B1-B2-B3-BN)(Duration-4) | (Volume-B1-B2-B3-BN)(Duration-4) | (Volume/Duration)*0.75
Number of C = Number of A (Medium Risk) |  |  | Medium Risk | C | TSSR Teams | A1/L7 | A2/L7 | A3/L3 | A4/L3 | A5/L3 | A6/L3 | C7 | C8 | C9 | C10 | C11 | C12
Number of C = Number of A (Low Risk) |  |  | Low Risk | C | TSSR Teams | A1/L6 | A2/L6 | A3/L2 | A4/L2 | A5/L2 | A6/L2 | C7 | C8 | C9 | C10 | C11 | C12
Number of C = Number of A (High Risk) |  |  | High Risk | C | TSSR Teams | A1/L8 | A2/L8 | A3/L4 | A4/L4 | A5/L4 | A6/L4 | C7 | C8 | C9 | C10 | C11 | C12
Number of C = Number of A (Very High Risk) |  |  | Very High Risk | C | TSSR Teams | A1/L9 | A2/L9 | A3/L5 | A4/L5 | A5/L5 | A6/L5 | C7 | C8 | C9 | C10 | C11 | C12
Number of D = Number of B (New-Low risk) |  | New | Low risk | D | SRAN Teams | B1/M6 | B2/M6 | B3/M6 | B4/M2 | B5/M2 | B6/M2 | B7/M2 | B8/M2 | B9/M2 | B10/M2 | B11/M2 | B12/M2
Number of D = Number of B (Exp-Low risk) |  | Exp | Low risk | D | SRAN Teams | B1/N6 | B2/N6 | B3/N6 | B4/N2 | B5/N2 | B6/N2 | B7/N2 | B8/N2 | B9/N2 | B10/N2 | B11/N2 | B12/N2
Number of D = Number of B (Swap-Low risk) |  | Swap | Low risk | D | SRAN Teams | B1/O6 | B2/O6 | B3/O6 | B4/O2 | B5/O2 | B6/O2 | B7/O2 | B8/O2 | B9/O2 | B10/O2 | B11/O2 | B12/O2
Number of D = Number of B (New-Medium risk) |  | New | Medium risk | D | SRAN Teams | B1/M7 | B2/M7 | B3/M7 | B4/M3 | B5/M3 | B6/M3 | B7/M3 | B8/M3 | B9/M3 | B10/M3 | B11/M3 | B12/M3
Number of D = Number of B (Exp-Medium risk) |  | Exp | Medium risk | D | SRAN Teams | B1/N7 | B2/N7 | B3/N7 | B4/N3 | B5/N3 | B6/N3 | B7/N3 | B8/N3 | B9/N3 | B10/N3 | B11/N3 | B12/N3
Number of D = Number of B (Swap-Medium risk) |  | Swap | Medium risk | D | SRAN Teams | B1/O7 | B2/O7 | B3/O7 | B4/O3 | B5/O3 | B6/O3 | B7/O3 | B8/O3 | B9/O3 | B10/O3 | B11/O3 | B12/O3
Number of D = Number of B (New-High risk) |  | New | High risk | D | SRAN Teams | B1/M8 | B2/M8 | B3/M8 | B4/M4 | B5/M4 | B6/M4 | B7/M4 | B8/M4 | B9/M4 | B10/M4 | B11/M4 | B12/M4
Number of D = Number of B (Exp-High risk) |  | Exp | High risk | D | SRAN Teams | B1/N8 | B2/N8 | B3/N8 | B4/N4 | B5/N4 | B6/N4 | B7/N4 | B8/N4 | B9/N4 | B10/N4 | B11/N4 | B12/N4
Number of D = Number of B (Swap-High risk) |  | Swap | High risk | D | SRAN Teams | B1/O8 | B2/O8 | B3/O8 | B4/O4 | B5/O4 | B6/O4 | B7/O4 | B8/O4 | B9/O4 | B10/O4 | B11/O4 | B12/O4
Number of D = Number of B (New-Very High risk) |  | New | Very High risk | D | SRAN Teams | B1/M9 | B2/M9 | B3/M9 | B4/M5 | B5/M5 | B6/M5 | B7/M5 | B8/M5 | B9/M5 | B10/M5 | B11/M5 | B12/M5
Number of D = Number of B (Exp-Very High risk) |  | Exp | Very High risk | D | SRAN Teams | B1/N9 | B2/N9 | B3/N9 | B4/N5 | B5/N5 | B6/N5 | B7/N5 | B8/N5 | B9/N5 | B10/N5 | B11/N5 | B12/N5
Number of D = Number of B (Swap-Very High risk) |  | Swap | Very High risk | D | SRAN Teams | B1/O9 | B2/O9 | B3/O9 | B4/O5 | B5/O5 | B6/O5 | B7/O5 | B8/O5 | B9/O5 | B10/O5 | B11/O5 | B12/O5
Number of E = Number B (New-Low risk) |  | New | Low risk | E | 5G Teams | B1/P6 | B2/P6 | B3/P6 | B4/P2 | B5/P2 | B6/P2 | B7/P2 | B8/P2 | B9/P2 | B10/P2 | B11/P2 | B12/P2
Number of E = Number B (EXP-Low risk) |  | EXP | Low risk | E | 5G Teams | B1/Q6 | B2/Q6 | B3/Q6 | B4/Q2 | B5/Q2 | B6/Q2 | B7/Q2 | B8/Q2 | B9/Q2 | B10/Q2 | B11/Q2 | B12/Q2
Number of E = Number B (Swap-Low risk) |  | Swap | Low risk | E | 5G Teams | B1/R6 | B2/R6 | B3/R6 | B4/R2 | B5/R2 | B6/R2 | B7/R2 | B8/R2 | B9/R2 | B10/R2 | B11/R2 | B12/R2
Number of E = Number B (New-Medium risk) |  | New | Medium risk | E | 5G Teams | B1/P7 | B2/P7 | B3/P7 | B4/P3 | B5/P3 | B6/P3 | B7/P3 | B8/P3 | B9/P3 | B10/P3 | B11/P3 | B12/P3
Number of E = Number B (EXP-Medium risk) |  | EXP | Medium risk | E | 5G Teams | B1/Q7 | B2/Q7 | B3/Q7 | B4/Q3 | B5/Q3 | B6/Q3 | B7/Q3 | B8/Q3 | B9/Q3 | B10/Q3 | B11/Q3 | B12/Q3
Number of E = Number B (Swap-Medium risk) |  | Swap | Medium risk | E | 5G Teams | B1/R7 | B2/R7 | B3/R7 | B4/R3 | B5/R3 | B6/R3 | B7/R3 | B8/R3 | B9/R3 | B10/R3 | B11/R3 | B12/R3
Number of E = Number B (New-High risk) |  | New | High risk | E | 5G Teams | B1/P8 | B2/P8 | B3/P8 | B4/P4 | B5/P4 | B6/P4 | B7/P4 | B8/P4 | B9/P4 | B10/P4 | B11/P4 | B12/P4
Number of E = Number B (EXP-High risk) |  | EXP | High risk | E | 5G Teams | B1/Q8 | B2/Q8 | B3/Q8 | B4/Q4 | B5/Q4 | B6/Q4 | B7/Q4 | B8/Q4 | B9/Q4 | B10/Q4 | B11/Q4 | B12/Q4
Number of E = Number B (SWAP-High risk) |  | SWAP | High risk | E | 5G Teams | B1/R8 | B2/R8 | B3/R8 | B4/R4 | B5/R4 | B6/R4 | B7/R4 | B8/R4 | B9/R4 | B10/R4 | B11/R4 | B12/R4
Number of E = Number B (New-Very High risk) |  | New | Very High risk | E | 5G Teams | B1/P9 | B2/P9 | B3/P9 | B4/P5 | B5/P5 | B6/P5 | B7/P5 | B8/P5 | B9/P5 | B10/P5 | B11/P5 | B12/P5
Number of E = Number B (EXP-Very High risk) |  | EXP | Very High risk | E | 5G Teams | B1/Q9 | B2/Q9 | B3/Q9 | B4/Q5 | B5/Q5 | B6/Q5 | B7/Q5 | B8/Q5 | B9/Q5 | B10/Q5 | B11/Q5 | B12/Q5
Number of E = Number B (SWAP-Very High risk) |  | SWAP | Very High risk | E | 5G Teams | B1/R9 | B2/R9 | B3/R9 | B4/R5 | B5/R5 | B6/R5 | B7/R5 | B8/R5 | B9/R5 | B10/R5 | B11/R5 | B12/R5
Number of F = Number B (New-Low Risk) |  | New | Low Risk | F | MW Teams | B1/S6 | B2/S6 | B3/S6 | B4/S2 | B5/S2 | B6/S2 | B7/S2 | B8/S2 | B9/S2 | B10/S2 | B11/S2 | B12/S2
Number of F = Number B (EXP-Low Risk) |  | EXP | Low Risk | F | MW Teams | B1/T6 | B2/T6 | B3/T6 | B4/T2 | B5/T2 | B6/T2 | B7/T2 | B8/T2 | B9/T2 | B10/T2 | B11/T2 | B12/T2
Number of F = Number B (Swap-Low Risk) |  | Swap | Low Risk | F | MW Teams | B1/U6 | B2/U6 | B3/U6 | B4/U2 | B5/U2 | B6/U2 | B7/U2 | B8/U2 | B9/U2 | B10/U2 | B11/U2 | B12/U2
Number of F = Number B (New-Medium Risk) |  | New | Medium Risk | F | MW Teams | B1/S7 | B2/S7 | B3/S7 | B4/S3 | B5/S3 | B6/S3 | B7/S3 | B8/S3 | B9/S3 | B10/S3 | B11/S3 | B12/S3
Number of F = Number B (EXP-Medium Risk) |  | EXP | Medium Risk | F | MW Teams | B1/T7 | B2/T7 | B3/T7 | B4/T3 | B5/T3 | B6/T3 | B7/T3 | B8/T3 | B9/T3 | B10/T3 | B11/T3 | B12/T3
Number of F = Number B (Swap-Medium Risk) |  | Swap | Medium Risk | F | MW Teams | B1/U7 | B2/U7 | B3/U7 | B4/U3 | B5/U3 | B6/U3 | B7/U3 | B8/U3 | B9/U3 | B10/U3 | B11/U3 | B12/U3
Number of F = Number B (New-High Risk) |  | New | High Risk | F | MW Teams | B1/S8 | B2/S8 | B3/S8 | B4/S4 | B5/S4 | B6/S4 | B7/S4 | B8/S4 | B9/S4 | B10/S4 | B11/S4 | B12/S4
Number of F = Number B (EXP-High Risk) |  | EXP | High Risk | F | MW Teams | B1/T8 | B2/T8 | B3/T8 | B4/T4 | B5/T4 | B6/T4 | B7/T4 | B8/T4 | B9/T4 | B10/T4 | B11/T4 | B12/T4
Number of F = Number B (SWAP-High Risk) |  | SWAP | High Risk | F | MW Teams | B1/U8 | B2/U8 | B3/U8 | B4/U4 | B5/U4 | B6/U4 | B7/U4 | B8/U4 | B9/U4 | B10/U4 | B11/U4 | B12/U4
Number of F = Number B (New-Very High Risk) |  | New | Very High Risk | F | MW Teams | B1/S9 | B2/S9 | B3/S9 | B4/S5 | B5/S5 | B6/S5 | B7/S5 | B8/S5 | B9/S5 | B10/S5 | B11/S5 | B12/S5
Number of F = Number B (Exp-Very High Risk) |  | Exp | Very High Risk | F | MW Teams | B1/T9 | B2/T9 | B3/T9 | B4/T5 | B5/T5 | B6/T5 | B7/T5 | B8/T5 | B9/T5 | B10/T5 | B11/T5 | B12/T5
Number of F = Number B (Swap-Very High Risk) |  | Swap | Very High Risk | F | MW Teams | B1/U9 | B2/U9 | B3/U9 | B4/U5 | B5/U5 | B6/U5 | B7/U5 | B8/U5 | B9/U5 | B10/U5 | B11/U5 | B12/U5
Number of G = Number of B (New-Low Risk) |  | New | Low Risk | G | CW Teams | B1/V6 | B2/V6 | B3/V6 | B4/V2 | B5/V2 | B6/V2 | B7/V2 | B8/V2 | B9/V2 | B10/V2 | B11/V2 | B12/V2
Number of G = Number of B (Exp-Low Risk) |  | Exp | Low Risk | G | CW Teams | B1/W6 | B2/W6 | B3/W6 | B4/W2 | B5/W2 | B6/W2 | B7/W2 | B8/W2 | B9/W2 | B10/W2 | B11/W2 | B12/W2
Number of G = Number of B (New-Medium Risk) |  | New | Medium Risk | G | CW Teams | B1/V7 | B2/V7 | B3/V7 | B4/V3 | B5/V3 | B6/V3 | B7/V3 | B8/V3 | B9/V3 | B10/V3 | B11/V3 | B12/V3
Number of G = Number of B (Exp-Medium Risk) |  | Exp | Medium Risk | G | CW Teams | B1/W7 | B2/W7 | B3/W7 | B4/W3 | B5/W3 | B6/W3 | B7/W3 | B8/W3 | B9/W3 | B10/W3 | B11/W3 | B12/W3
Number of G = Number of B (New-High Risk) |  | New | High Risk | G | CW Teams | B1/V8 | B2/V8 | B3/V8 | B4/V4 | B5/V4 | B6/V4 | B7/V4 | B8/V4 | B9/V4 | B10/V4 | B11/V4 | B12/V4
Number of G = Number of B (Exp-High Risk) |  | Exp | High Risk | G | CW Teams | B1/W8 | B2/W8 | B3/W8 | B4/W4 | B5/W4 | B6/W4 | B7/W4 | B8/W4 | B9/W4 | B10/W4 | B11/W4 | B12/W4
Number of G = Number of B (New-Very High Risk) |  | New | Very High Risk | G | CW Teams | B1/V9 | B2/V9 | B3/V9 | B4/V5 | B5/V5 | B6/V5 | B7/V5 | B8/V5 | B9/V5 | B10/V5 | B11/V5 | B12/V5
Number of G = Number of B (Exp-Very High Risk) |  | Exp | Very High Risk | G | CW Teams | B1/W9 | B2/W9 | B3/W9 | B4/W5 | B5/W5 | B6/W5 | B7/W5 | B8/W5 | B9/W5 | B10/W5 | B11/W5 | B12/W5
Number of H = Number of B | In case of result Less than 1 consider 1 |  |  | H | Supervisors | (D1+E1+F1+G1)/4 | (D2+E2+F2+G2)/4 | (D3+E3+F3+G3)/4 | (D4+E4+F4+G4)/4 | (D5+E5+F5+G5)/4 | (D6+E6+F6+G6)/4 | (D7+E7+F7+G7)/4 | (D8+E8+F8+G8)/4 | (D9+E9+F9+G9)/4 | (D10+E10+F10+G10)/4 | (D11+E11+F11+G11)/4 | (D12+E12+F12+G12)/4
Number of I = Number of B | In case of result Less than 1 consider 1 |  |  | I | FDM | H1/4 | H2/4 | H3/4 | H4/4 | H5/4 | H6/4 | H7/4 | H8/4 | H9/4 | H10/4 | H11/4 | H12/4
Number of AE = Number of B | In case of result Less than 1 consider 1, for SRAN,5G,MW |  |  | AE | RIC Engineer | B1/100 | B2/100 | B3/100 | B4/100 | B5/100 | B6/100 | B7/100 | B8/100 | B9/100 | B10/100 | B11/100 | B12/100
Number of AE = Number of B | In case of result Less than 1 consider 0, for CW |  |  | AE | RIC Engineer | B1/100 | B2/100 | B3/100 | B4/100 | B5/100 | B6/100 | B7/100 | B8/100 | B9/100 | B10/100 | B11/100 | B12/100
Number of J = Number of B | In case of result Less than 1 consider 1 |  |  | J | ROM | I1/3 | I2/3 | I3/3 | I4/3 | I5/3 | I6/3 | I7/3 | I8/3 | I9/3 | I10/3 | I11/3 | I12/3
Number of K = Number of B | In case of result Less than 1 consider 1 |  |  | K | PM | J1/3 | J2/3 | J3/3 | J4/3 | J5/3 | J6/3 | J7/3 | J8/3 | J9/3 | J10/3 | J11/3 | J12/3
Number of X = Number of B | In case of result Less than 1 consider 1 |  |  | X | QHSE Auditor | B1/200 | B2/200 | B3/200 | B4/200 | B5/200 | B6/200 | B7/200 | B8/200 | B9/200 | B10/200 | B11/200 | B12/200
Number of Y = Number of B | In case of result Less than 1 consider 1 |  |  | Y | Project Coordinator | B1/150 | B2/150 | B3/150 | B4/150 | B5/150 | B6/150 | B7/150 | B8/150 | B9/150 | B10/150 | B11/150 | B12/150
Number of Z = Number of B | In case of result Less than 1 consider 1 |  |  | Z | Site Engineering | B1/150 | B2/150 | B3/150 | B4/150 | B5/150 | B6/150 | B7/150 | B8/150 | B9/150 | B10/150 | B11/150 | B12/150
Number of AA = Number of B | In case of result Less than 1 consider 1 |  |  | AA | Materials Manager | B1/150 | B2/150 | B3/150 | B4/150 | B5/150 | B6/150 | B7/150 | B8/150 | B9/150 | B10/150 | B11/150 | B12/150
Number of AB= Number of B | In case of result Less than 1 consider 1 |  |  | AB | Acceptance Manager | J1/3 | J2/3 | J3/3 | J4/3 | J5/3 | J6/3 | J7/3 | J8/3 | J9/3 | J10/3 | J11/3 | J12/3
Number of AC = Number of B | In case of result Less than 1 consider 1 |  |  | AC | Acceptance supervisor | B1/75 | B2/75 | B3/75 | B4/75 | B5/75 | B6/75 | B7/75 | B8/75 | B9/75 | B10/75 | B11/75 | B12/75
Number of AD = Number of B | In case of result Less than 1 consider 1 |  |  | AD | SAQ coordinator | B1/150 | B2/150 | B3/150 | B4/150 | B5/150 | B6/150 | B7/150 | B8/150 | B9/150 | B10/150 | B11/150 | B12/150

## Formula
Milestone/teams | P1 | P2 | P3 | P4 | P5 | P6 | P7 | P8 | P9 | P10 | P11 | P12 | Number of B = Duarion |  | Number of D = Number of B (New-Low risk) |  | Number of E = Number B (New-Low risk) |  | Number of F = Number B (New-Low Risk) |  | Number of G = Number of B (New-Low Risk) |  | Number of H = Number of B |  | column | SCOPE | SCOPE TYPE | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
TSSR PIP | A1 | A2 | A3 | A4 | A5 | A6 | A7 | A8 | A9 | A10 | A11 | A12 | B1 | (Volume/Duration)*0.25 | D1 | B1/M6 | E1 | B1/P6 | F1 | B1/S6 | G1 | B1/V6 | H1 | (D1+E1+F1+G1)/4
RO PIP | B1 | B2 | B3 | B4 | B5 | B6 | B7 | B8 | B9 | B10 | B11 | B12 | B2 | (Volume/Duration)*0.5 | D2 | B2/M6 | E2 | B2/P6 | F2 | B2/S6 | G2 | B2/V6 | H2 | (D2+E2+F2+G2)/4 |  |  |  |  | Bussiness as usual |  |  |  | Start Up
TSSR Teams | C1 | C2 | C3 | C4 | C5 | C6 | C7 | C8 | C9 | C10 | C11 | C12 | B3 | (Volume/Duration)*0.75 | D3 | B3/M6 | E3 | B3/P6 | F3 | B3/S6 | G3 | B3/V6 | H3 | (D3+E3+F3+G3)/4 |  |  |  |  | Low Risk | Medium Risk | High Risk | Very High risk | Low Risk | Medium Risk | High Risk | Very High risk
SRAN Teams | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | B4 | (Volume-B1-B2-B3-BN)(Duration-4) | D4 | B4/M2 | E4 | B4/P2 | F4 | B4/S2 | G4 | B4/V2 | H4 | (D4+E4+F4+G4)/4 |  |  |  | Duration | Productivity/Month | Productivity/Month | Productivity/Month | Productivity/Month | Productivity/Month | Productivity/Month | Productivity/Month | Productivity/Month
5G Teams | E1 | E2 | E3 | E4 | E5 | E6 | E7 | E8 | E9 | E10 | E11 | E12 | B5 | (Volume-B1-B2-B3-BN)(Duration-4) | D5 | B5/M2 | E5 | B5/P2 | F5 | B5/S2 | G5 | B5/V2 | H5 | (D5+E5+F5+G5)/4 | L | TSSR | All | 0.5 | 48 | 38.4 | 32 | 24 | 32 | 25.6 | 21.3333 | 16
MW Teams | F1 | F2 | F3 | F4 | F5 | F6 | F7 | F8 | F9 | F10 | F11 | F12 | B6 | (Volume-B1-B2-B3-BN)(Duration-4) | D6 | B6/M2 | E6 | B6/P2 | F6 | B6/S2 | G6 | B6/V2 | H6 | (D6+E6+F6+G6)/4 | M | SRAN | NEW | 4 | 6 | 4.8 | 4 | 3 | 4 | 3.2 | 2.6667 | 2
CW Teams | G1 | G2 | G3 | G4 | G5 | G6 | G7 | G8 | G9 | G10 | G11 | G12 | B7 | (Volume-B1-B2-B3-BN)(Duration-4) | D7 | B7/M2 | E7 | B7/P2 | F7 | B7/S2 | G7 | B7/V2 | H7 | (D7+E7+F7+G7)/4 | N | SRAN | Expansion | 3 | 8 | 6.4 | 5.3333 | 4 | 5.3333 | 4.2667 | 3.5556 | 2.6667
Supervisors | H1 | H2 | H3 | H4 | H5 | H6 | H7 | H8 | H9 | H10 | H11 | H12 | B8 | (Volume-B1-B2-B3-BN)(Duration-4) | D8 | B8/M2 | E8 | B8/P2 | F8 | B8/S2 | G8 | B8/V2 | H8 | (D8+E8+F8+G8)/4 | O | SRAN | Swap | 5 | 4.8 | 3.84 | 3.2 | 2.4 | 3.2 | 2.56 | 2.1333 | 1.6
FDM | I1 | I2 | I3 | I4 | I5 | I6 | I7 | I8 | I9 | I10 | I11 | I12 | B9 | (Volume-B1-B2-B3-BN)(Duration-4) | D9 | B9/M2 | E9 | B9/P2 | F9 | B9/S2 | G9 | B9/V2 | H9 | (D9+E9+F9+G9)/4 | P | 5G | NEW | 3 | 8 | 6.4 | 5.3333 | 4 | 5.3333 | 4.2667 | 3.5556 | 2.6667
RIC Engineer | AE1 | AE2 | AE3 | AE4 | AE5 | AE6 | AE7 | AE8 | AE9 | AE10 | AE11 | AE12 | B10 | (Volume-B1-B2-B3-BN)(Duration-4) | D10 | B10/M2 | E10 | B10/P2 | F10 | B10/S2 | G10 | B10/V2 | H10 | (D10+E10+F10+G10)/4 | Q | 5G | Expansion | 3 | 8 | 6.4 | 5.3333 | 4 | 5.3333 | 4.2667 | 3.5556 | 2.6667
ROM | J1 | J2 | J3 | J4 | J5 | J6 | J7 | J8 | J9 | J10 | J11 | J12 | B11 | (Volume-B1-B2-B3-BN)(Duration-4) | D11 | B11/M2 | E11 | B11/P2 | F11 | B11/S2 | G11 | B11/V2 | H11 | (D11+E11+F11+G11)/4 | R | 5G | Swap | 4 | 6 | 4.8 | 4 | 3 | 4 | 3.2 | 2.6667 | 2
PM | K1 | K2 | K3 | K4 | K5 | K6 | K7 | K8 | K9 | K10 | K11 | K12 | B12 | (Volume/Duration)*0.75 | D12 | B12/M2 | E12 | B12/P2 | F12 | B12/S2 | G12 | B12/V2 | H12 | (D12+E12+F12+G12)/4 | S | MW | NEW | 3 | 8 | 6.4 | 5.3333 | 4 | 5.3333 | 4.2667 | 3.5556 | 2.6667
QHSE Auditor | X1 | X2 | X3 | X4 | X5 | X6 | X7 | X8 | X9 | X10 | X11 | X12 | [10 empty] | In case of result Less than 1 consider 1 |  | T | MW | Expansion | 3 | 8 | 6.4 | 5.3333 | 4 | 5.3333 | 4.2667 | 3.5556 | 2.6667
Project Coordinator | Y1 | Y2 | Y3 | Y4 | Y5 | Y6 | Y7 | Y8 | Y9 | Y10 | Y11 | Y12 | Number of A =Duration/2 |  | Number of D = Number of B (Exp-Low risk) |  | Number of E = Number B (EXP-Low risk) |  | Number of F = Number B (EXP-Low Risk) |  | Number of G = Number of B (Exp-Low Risk) |  |  |  | U | MW | Swap | 4 | 6 | 4.8 | 4 | 3 | 4 | 3.2 | 2.6667 | 2
Site Engineering | Z1 | Z2 | Z3 | Z4 | Z5 | Z6 | Z7 | Z8 | Z9 | Z10 | Z11 | Z12 | A1 | B1+B2 | D1 | B1/N6 | E1 | B1/Q6 | F1 | B1/T6 | G1 | B1/W6 | Number of I = Number of B |  | V | CW | New | 10 | 2.4 | 1.92 | 1.6 | 1.2 | 1.6 | 1.28 | 1.0667 | 0.8
Materials Manager | AA1 | AA2 | AA3 | AA4 | AA5 | AA6 | AA7 | AA8 | AA9 | AA10 | AA11 | AA12 | A2 | B3+B4 | D2 | B2/N6 | E2 | B2/Q6 | F2 | B2/T6 | G2 | B2/W6 | I1 | H1/4 | W | CW | Expansion | 3 | 8 | 6.4 | 5.3333 | 4 | 5.3333 | 4.2667 | 3.5556 | 2.6667
Acceptance Manager | AB1 | AB2 | AB3 | AB4 | AB5 | AB6 | AB7 | AB8 | AB9 | AB10 | AB11 | AB12 | A3 | B5+B6 | D3 | B3/N6 | E3 | B3/Q6 | F3 | B3/T6 | G3 | B3/W6 | I2 | H2/4
Acceptance supervisor | AC1 | AC2 | AC3 | AC4 | AC5 | AC6 | AC7 | AC8 | AC9 | AC10 | AC11 | AC12 | A4 | B7+B8 | D4 | B4/N2 | E4 | B4/Q2 | F4 | B4/T2 | G4 | B4/W2 | I3 | H3/4
SAQ coordinator | AD1 | AD2 | AD3 | AD4 | AD5 | AD6 | AD7 | AD8 | AD9 | AD10 | AD11 | AD12 | A5 | B9+B10 | D5 | B5/N2 | E5 | B5/Q2 | F5 | B5/T2 | G5 | B5/W2 | I4 | H4/4
[13 empty] | A6 | B11+B12 | D6 | B6/N2 | E6 | B6/Q2 | F6 | B6/T2 | G6 | B6/W2 | I5 | H5/4
[15 empty] | D7 | B7/N2 | E7 | B7/Q2 | F7 | B7/T2 | G7 | B7/W2 | I6 | H6/4
[13 empty] | Number of C = Number of A (Medium Risk) |  | D8 | B8/N2 | E8 | B8/Q2 | F8 | B8/T2 | G8 | B8/W2 | I7 | H7/4
[13 empty] | C1 | A1/L7 | D9 | B9/N2 | E9 | B9/Q2 | F9 | B9/T2 | G9 | B9/W2 | I8 | H8/4
[13 empty] | C2 | A2/L7 | D10 | B10/N2 | E10 | B10/Q2 | F10 | B10/T2 | G10 | B10/W2 | I9 | H9/4
[13 empty] | C3 | A3/L3 | D11 | B11/N2 | E11 | B11/Q2 | F11 | B11/T2 | G11 | B11/W2 | I10 | H10/4
[13 empty] | C4 | A4/L3 | D12 | B12/N2 | E12 | B12/Q2 | F12 | B12/T2 | G12 | B12/W2 | I11 | H11/4
[13 empty] | C5 | A5/L3 | [8 empty] | I12 | H12/4
[13 empty] | C6 | A6/L3 | Number of D = Number of B (Swap-Low risk) |  | Number of E = Number B (Swap-Low risk) |  | Number of F = Number B (Swap-Low Risk) |  | Number of G = Number of B (New-Medium Risk) |  | In case of result Less than 1 consider 1
[15 empty] | D1 | B1/O6 | E1 | B1/R6 | F1 | B1/U6 | G1 | B1/V7
[13 empty] | Number of C = Number of A (Low Risk) |  | D2 | B2/O6 | E2 | B2/R6 | F2 | B2/U6 | G2 | B2/V7 | Number of J = Number of B
[13 empty] | C1 | A1/L6 | D3 | B3/O6 | E3 | B3/R6 | F3 | B3/U6 | G3 | B3/V7 | J1 | I1/3 (Project#1,2,3,4)
[13 empty] | C2 | A2/L6 | D4 | B4/O2 | E4 | B4/R2 | F4 | B4/U2 | G4 | B4/V3 | J2 | I2/3 (Project#1,2,3,4)
[13 empty] | C3 | A3/L2 | D5 | B5/O2 | E5 | B5/R2 | F5 | B5/U2 | G5 | B5/V3 | J3 | I3/3 (Project#1,2,3,4)
[13 empty] | C4 | A4/L2 | D6 | B6/O2 | E6 | B6/R2 | F6 | B6/U2 | G6 | B6/V3 | J4 | I4/3 (Project#1,2,3,4)
[13 empty] | C5 | A5/L2 | D7 | B7/O2 | E7 | B7/R2 | F7 | B7/U2 | G7 | B7/V3 | J5 | I5/3 (Project#1,2,3,4)
[13 empty] | C6 | A6/L2 | D8 | B8/O2 | E8 | B8/R2 | F8 | B8/U2 | G8 | B8/V3 | J6 | I6/3 (Project#1,2,3,4)
[15 empty] | D9 | B9/O2 | E9 | B9/R2 | F9 | B9/U2 | G9 | B9/V3 | J7 | I7/3 (Project#1,2,3,4)
[13 empty] | Number of C = Number of A (High Risk) |  | D10 | B10/O2 | E10 | B10/R2 | F10 | B10/U2 | G10 | B10/V3 | J8 | I8/3 (Project#1,2,3,4)
[13 empty] | C1 | A1/L8 | D11 | B11/O2 | E11 | B11/R2 | F11 | B11/U2 | G11 | B11/V3 | J9 | I9/3 (Project#1,2,3,4)
[13 empty] | C2 | A2/L8 | D12 | B12/O2 | E12 | B12/R2 | F12 | B12/U2 | G12 | B12/V3 | J10 | I10/3 (Project#1,2,3,4)
[13 empty] | C3 | A3/L4 | [8 empty] | J11 | I11/3 (Project#1,2,3,4)
[13 empty] | C4 | A4/L4 | Number of D = Number of B (New-Medium risk) |  | Number of E = Number B (New-Medium risk) |  | Number of F = Number B (New-Medium Risk) |  | Number of G = Number of B (Exp-Medium Risk) |  | J12 | I12/3 (Project#1,2,3,4)
[13 empty] | C5 | A5/L4 | D1 | B1/M7 | E1 | B1/P7 | F1 | B1/S7 | G1 | B1/W7 | In case of result Less than 1 consider 1
[13 empty] | C6 | A6/L4 | D2 | B2/M7 | E2 | B2/P7 | F2 | B2/S7 | G2 | B2/W7
[15 empty] | D3 | B3/M7 | E3 | B3/P7 | F3 | B3/S7 | G3 | B3/W7 | Number of K = Number of B
[13 empty] | Number of C = Number of A (Very High Risk) |  | D4 | B4/M3 | E4 | B4/P3 | F4 | B4/S3 | G4 | B4/W3 | K1 | J1/3 (Project#1,2,3,4)
[13 empty] | C1 | A1/L9 | D5 | B5/M3 | E5 | B5/P3 | F5 | B5/S3 | G5 | B5/W3 | K2 | J2/3 (Project#1,2,3,4)
[13 empty] | C2 | A2/L9 | D6 | B6/M3 | E6 | B6/P3 | F6 | B6/S3 | G6 | B6/W3 | K3 | J3/3 (Project#1,2,3,4)
[13 empty] | C3 | A3/L5 | D7 | B7/M3 | E7 | B7/P3 | F7 | B7/S3 | G7 | B7/W3 | K4 | J4/3 (Project#1,2,3,4)
[13 empty] | C4 | A4/L5 | D8 | B8/M3 | E8 | B8/P3 | F8 | B8/S3 | G8 | B8/W3 | K5 | J5/3 (Project#1,2,3,4)
[13 empty] | C5 | A5/L5 | D9 | B9/M3 | E9 | B9/P3 | F9 | B9/S3 | G9 | B9/W3 | K6 | J6/3 (Project#1,2,3,4)
[13 empty] | C6 | A6/L5 | D10 | B10/M3 | E10 | B10/P3 | F10 | B10/S3 | G10 | B10/W3 | K7 | J7/3 (Project#1,2,3,4)
[15 empty] | D11 | B11/M3 | E11 | B11/P3 | F11 | B11/S3 | G11 | B11/W3 | K8 | J8/3 (Project#1,2,3,4)
[15 empty] | D12 | B12/M3 | E12 | B12/P3 | F12 | B12/S3 | G12 | B12/W3 | K9 | J9/3 (Project#1,2,3,4)
[23 empty] | K10 | J10/3 (Project#1,2,3,4)
[15 empty] | Number of D = Number of B (Exp-Medium risk) |  | Number of E = Number B (EXP-Medium risk) |  | Number of F = Number B (EXP-Medium Risk) |  |  |  | K11 | J11/3 (Project#1,2,3,4)
[15 empty] | D1 | B1/N7 | E1 | B1/Q7 | F1 | B1/T7 | Number of G = Number of B (New-High Risk) |  | K12 | J12/3 (Project#1,2,3,4)
[15 empty] | D2 | B2/N7 | E2 | B2/Q7 | F2 | B2/T7 | G1 | B1/V8 | In case of result Less than 1 consider 1
[15 empty] | D3 | B3/N7 | E3 | B3/Q7 | F3 | B3/T7 | G2 | B2/V8
[15 empty] | D4 | B4/N3 | E4 | B4/Q3 | F4 | B4/T3 | G3 | B3/V8 | Number of X = Number of B
[15 empty] | D5 | B5/N3 | E5 | B5/Q3 | F5 | B5/T3 | G4 | B4/V4 | X1 | B1/200 (ProBect#1,2,3,4)
[15 empty] | D6 | B6/N3 | E6 | B6/Q3 | F6 | B6/T3 | G5 | B5/V4 | X2 | B2/200 (ProBect#1,2,3,4)
[15 empty] | D7 | B7/N3 | E7 | B7/Q3 | F7 | B7/T3 | G6 | B6/V4 | X3 | B3/200 (ProBect#1,2,3,4)
[15 empty] | D8 | B8/N3 | E8 | B8/Q3 | F8 | B8/T3 | G7 | B7/V4 | X4 | B4/200 (ProBect#1,2,3,4)
[15 empty] | D9 | B9/N3 | E9 | B9/Q3 | F9 | B9/T3 | G8 | B8/V4 | X5 | B5/200 (ProBect#1,2,3,4)
[15 empty] | D10 | B10/N3 | E10 | B10/Q3 | F10 | B10/T3 | G9 | B9/V4 | X6 | B6/200 (ProBect#1,2,3,4)
[15 empty] | D11 | B11/N3 | E11 | B11/Q3 | F11 | B11/T3 | G10 | B10/V4 | X7 | B7/200 (ProBect#1,2,3,4)
[15 empty] | D12 | B12/N3 | E12 | B12/Q3 | F12 | B12/T3 | G11 | B11/V4 | X8 | B8/200 (ProBect#1,2,3,4)
[21 empty] | G12 | B12/V4 | X9 | B9/200 (ProBect#1,2,3,4)
[15 empty] | Number of D = Number of B (Swap-Medium risk) |  | Number of E = Number B (Swap-Medium risk) |  | Number of F = Number B (Swap-Medium Risk) |  |  |  | X10 | B10/200 (ProBect#1,2,3,4)
[15 empty] | D1 | B1/O7 | E1 | B1/R7 | F1 | B1/U7 | Number of G = Number of B (Exp-High Risk) |  | X11 | B11/200 (ProBect#1,2,3,4)
[15 empty] | D2 | B2/O7 | E2 | B2/R7 | F2 | B2/U7 | G1 | B1/W8 | X12 | B12/200 (ProBect#1,2,3,4)
[15 empty] | D3 | B3/O7 | E3 | B3/R7 | F3 | B3/U7 | G2 | B2/W8 | In case of result Less than 1 consider 1
[15 empty] | D4 | B4/O3 | E4 | B4/R3 | F4 | B4/U3 | G3 | B3/W8
[15 empty] | D5 | B5/O3 | E5 | B5/R3 | F5 | B5/U3 | G4 | B4/W4 | Number of Y = Number of B
[15 empty] | D6 | B6/O3 | E6 | B6/R3 | F6 | B6/U3 | G5 | B5/W4 | Y1 | B1/150 (ProBect#1,2,3,4)
[15 empty] | D7 | B7/O3 | E7 | B7/R3 | F7 | B7/U3 | G6 | B6/W4 | Y2 | B2/150 (ProBect#1,2,3,4)
[15 empty] | D8 | B8/O3 | E8 | B8/R3 | F8 | B8/U3 | G7 | B7/W4 | Y3 | B3/150 (ProBect#1,2,3,4)
[15 empty] | D9 | B9/O3 | E9 | B9/R3 | F9 | B9/U3 | G8 | B8/W4 | Y4 | B4/150 (ProBect#1,2,3,4)
[15 empty] | D10 | B10/O3 | E10 | B10/R3 | F10 | B10/U3 | G9 | B9/W4 | Y5 | B5/150 (ProBect#1,2,3,4)
[15 empty] | D11 | B11/O3 | E11 | B11/R3 | F11 | B11/U3 | G10 | B10/W4 | Y6 | B6/150 (ProBect#1,2,3,4)
[15 empty] | D12 | B12/O3 | E12 | B12/R3 | F12 | B12/U3 | G11 | B11/W4 | Y7 | B7/150 (ProBect#1,2,3,4)
[21 empty] | G12 | B12/W4 | Y8 | B8/150 (ProBect#1,2,3,4)
[15 empty] | Number of D = Number of B (New-High risk) |  | Number of E = Number B (New-High risk) |  | Number of F = Number B (New-High Risk) |  |  |  | Y9 | B9/150 (ProBect#1,2,3,4)
[15 empty] | D1 | B1/M8 | E1 | B1/P8 | F1 | B1/S8 |  |  | Y10 | B10/150 (ProBect#1,2,3,4)
[15 empty] | D2 | B2/M8 | E2 | B2/P8 | F2 | B2/S8 | Number of G = Number of B (New-Very High Risk) |  | Y11 | B11/150 (ProBect#1,2,3,4)
[15 empty] | D3 | B3/M8 | E3 | B3/P8 | F3 | B3/S8 | G1 | B1/V9 | Y12 | B12/150 (ProBect#1,2,3,4)
[15 empty] | D4 | B4/M4 | E4 | B4/P4 | F4 | B4/S4 | G2 | B2/V9 | In case of result Less than 1 consider 1
[15 empty] | D5 | B5/M4 | E5 | B5/P4 | F5 | B5/S4 | G3 | B3/V9
[15 empty] | D6 | B6/M4 | E6 | B6/P4 | F6 | B6/S4 | G4 | B4/V5 | Number of Z = Number of B
[15 empty] | D7 | B7/M4 | E7 | B7/P4 | F7 | B7/S4 | G5 | B5/V5 | Z1 | B1/150 (ProBect#1,2,3,4)
[15 empty] | D8 | B8/M4 | E8 | B8/P4 | F8 | B8/S4 | G6 | B6/V5 | Z2 | B2/150 (ProBect#1,2,3,4)
[15 empty] | D9 | B9/M4 | E9 | B9/P4 | F9 | B9/S4 | G7 | B7/V5 | Z3 | B3/150 (ProBect#1,2,3,4)
[15 empty] | D10 | B10/M4 | E10 | B10/P4 | F10 | B10/S4 | G8 | B8/V5 | Z4 | B4/150 (ProBect#1,2,3,4)
[15 empty] | D11 | B11/M4 | E11 | B11/P4 | F11 | B11/S4 | G9 | B9/V5 | Z5 | B5/150 (ProBect#1,2,3,4)
[15 empty] | D12 | B12/M4 | E12 | B12/P4 | F12 | B12/S4 | G10 | B10/V5 | Z6 | B6/150 (ProBect#1,2,3,4)
[21 empty] | G11 | B11/V5 | Z7 | B7/150 (ProBect#1,2,3,4)
[15 empty] | Number of D = Number of B (Exp-High risk) |  | Number of E = Number B (EXP-High risk) |  | Number of F = Number B (EXP-High Risk) |  | G12 | B12/V5 | Z8 | B8/150 (ProBect#1,2,3,4)
[15 empty] | D1 | B1/N8 | E1 | B1/Q8 | F1 | B1/T8 |  |  | Z9 | B9/150 (ProBect#1,2,3,4)
[15 empty] | D2 | B2/N8 | E2 | B2/Q8 | F2 | B2/T8 | Number of G = Number of B (Exp-Very High Risk) |  | Z10 | B10/150 (ProBect#1,2,3,4)
[15 empty] | D3 | B3/N8 | E3 | B3/Q8 | F3 | B3/T8 | G1 | B1/W9 | Z11 | B11/150 (ProBect#1,2,3,4)
[15 empty] | D4 | B4/N4 | E4 | B4/Q4 | F4 | B4/T4 | G2 | B2/W9 | Z12 | B12/150 (ProBect#1,2,3,4)
[15 empty] | D5 | B5/N4 | E5 | B5/Q4 | F5 | B5/T4 | G3 | B3/W9 | In case of result Less than 1 consider 1
[15 empty] | D6 | B6/N4 | E6 | B6/Q4 | F6 | B6/T4 | G4 | B4/W5
[15 empty] | D7 | B7/N4 | E7 | B7/Q4 | F7 | B7/T4 | G5 | B5/W5 | Number of AA = Number of B
[15 empty] | D8 | B8/N4 | E8 | B8/Q4 | F8 | B8/T4 | G6 | B6/W5 | AA1 | B1/150 (ProBect#1,2,3,4)
[15 empty] | D9 | B9/N4 | E9 | B9/Q4 | F9 | B9/T4 | G7 | B7/W5 | AA2 | B2/150 (ProBect#1,2,3,4)
[15 empty] | D10 | B10/N4 | E10 | B10/Q4 | F10 | B10/T4 | G8 | B8/W5 | AA3 | B3/150 (ProBect#1,2,3,4)
[15 empty] | D11 | B11/N4 | E11 | B11/Q4 | F11 | B11/T4 | G9 | B9/W5 | AA4 | B4/150 (ProBect#1,2,3,4)
[15 empty] | D12 | B12/N4 | E12 | B12/Q4 | F12 | B12/T4 | G10 | B10/W5 | AA5 | B5/150 (ProBect#1,2,3,4)
[21 empty] | G11 | B11/W5 | AA6 | B6/150 (ProBect#1,2,3,4)
[15 empty] | Number of D = Number of B (Swap-High risk) |  | Number of E = Number B (SWAP-High risk) |  | Number of F = Number B (SWAP-High Risk) |  | G12 | B12/W5 | AA7 | B7/150 (ProBect#1,2,3,4)
[15 empty] | D1 | B1/O8 | E1 | B1/R8 | F1 | B1/U8 |  |  | AA8 | B8/150 (ProBect#1,2,3,4)
[15 empty] | D2 | B2/O8 | E2 | B2/R8 | F2 | B2/U8 |  |  | AA9 | B9/150 (ProBect#1,2,3,4)
[15 empty] | D3 | B3/O8 | E3 | B3/R8 | F3 | B3/U8 |  |  | AA10 | B10/150 (ProBect#1,2,3,4)
[15 empty] | D4 | B4/O4 | E4 | B4/R4 | F4 | B4/U4 |  |  | AA11 | B11/150 (ProBect#1,2,3,4)
[15 empty] | D5 | B5/O4 | E5 | B5/R4 | F5 | B5/U4 |  |  | AA12 | B12/150 (ProBect#1,2,3,4)
[15 empty] | D6 | B6/O4 | E6 | B6/R4 | F6 | B6/U4 |  |  | In case of result Less than 1 consider 1
[15 empty] | D7 | B7/O4 | E7 | B7/R4 | F7 | B7/U4
[15 empty] | D8 | B8/O4 | E8 | B8/R4 | F8 | B8/U4 |  |  | Number of AB= Number of B
[15 empty] | D9 | B9/O4 | E9 | B9/R4 | F9 | B9/U4 |  |  | AB1 | J1/3 (Project#1,2,3,4)
[15 empty] | D10 | B10/O4 | E10 | B10/R4 | F10 | B10/U4 |  |  | AB2 | J2/3 (Project#1,2,3,4)
[15 empty] | D11 | B11/O4 | E11 | B11/R4 | F11 | B11/U4 |  |  | AB3 | J3/3 (Project#1,2,3,4)
[15 empty] | D12 | B12/O4 | E12 | B12/R4 | F12 | B12/U4 |  |  | AB4 | J4/3 (Project#1,2,3,4)
[23 empty] | AB5 | J5/3 (Project#1,2,3,4)
[15 empty] | Number of D = Number of B (New-Very High risk) |  | Number of E = Number B (New-Very High risk) |  | Number of F = Number B (New-Very High Risk) |  |  |  | AB6 | J6/3 (Project#1,2,3,4)
[15 empty] | D1 | B1/M9 | E1 | B1/P9 | F1 | B1/S9 |  |  | AB7 | J7/3 (Project#1,2,3,4)
[15 empty] | D2 | B2/M9 | E2 | B2/P9 | F2 | B2/S9 |  |  | AB8 | J8/3 (Project#1,2,3,4)
[15 empty] | D3 | B3/M9 | E3 | B3/P9 | F3 | B3/S9 |  |  | AB9 | J9/3 (Project#1,2,3,4)
[15 empty] | D4 | B4/M5 | E4 | B4/P5 | F4 | B4/S5 |  |  | AB10 | J10/3 (Project#1,2,3,4)
[15 empty] | D5 | B5/M5 | E5 | B5/P5 | F5 | B5/S5 |  |  | AB11 | J11/3 (Project#1,2,3,4)
[15 empty] | D6 | B6/M5 | E6 | B6/P5 | F6 | B6/S5 |  |  | AB12 | J12/3 (Project#1,2,3,4)
[15 empty] | D7 | B7/M5 | E7 | B7/P5 | F7 | B7/S5 |  |  | In case of result Less than 1 consider 1
[15 empty] | D8 | B8/M5 | E8 | B8/P5 | F8 | B8/S5
[15 empty] | D9 | B9/M5 | E9 | B9/P5 | F9 | B9/S5 |  |  | Number of AC = Number of B
[15 empty] | D10 | B10/M5 | E10 | B10/P5 | F10 | B10/S5 |  |  | AC1 | B1/75 (ProBect#1,2,3,4)
[15 empty] | D11 | B11/M5 | E11 | B11/P5 | F11 | B11/S5 |  |  | AC2 | B2/75 (ProBect#1,2,3,4)
[15 empty] | D12 | B12/M5 | E12 | B12/P5 | F12 | B12/S5 |  |  | AC3 | B3/75 (ProBect#1,2,3,4)
[23 empty] | AC4 | B4/75 (ProBect#1,2,3,4)
[15 empty] | Number of D = Number of B (Exp-Very High risk) |  | Number of E = Number B (EXP-Very High risk) |  | Number of F = Number B (Exp-Very High Risk) |  |  |  | AC5 | B5/75 (ProBect#1,2,3,4)
[15 empty] | D1 | B1/N9 | E1 | B1/Q9 | F1 | B1/T9 |  |  | AC6 | B6/75 (ProBect#1,2,3,4)
[15 empty] | D2 | B2/N9 | E2 | B2/Q9 | F2 | B2/T9 |  |  | AC7 | B7/75 (ProBect#1,2,3,4)
[15 empty] | D3 | B3/N9 | E3 | B3/Q9 | F3 | B3/T9 |  |  | AC8 | B8/75 (ProBect#1,2,3,4)
[15 empty] | D4 | B4/N5 | E4 | B4/Q5 | F4 | B4/T5 |  |  | AC9 | B9/75 (ProBect#1,2,3,4)
[15 empty] | D5 | B5/N5 | E5 | B5/Q5 | F5 | B5/T5 |  |  | AC10 | B10/75 (ProBect#1,2,3,4)
[15 empty] | D6 | B6/N5 | E6 | B6/Q5 | F6 | B6/T5 |  |  | AC11 | B11/75 (ProBect#1,2,3,4)
[15 empty] | D7 | B7/N5 | E7 | B7/Q5 | F7 | B7/T5 |  |  | AC12 | B12/75 (ProBect#1,2,3,4)
[15 empty] | D8 | B8/N5 | E8 | B8/Q5 | F8 | B8/T5 |  |  | In case of result Less than 1 consider 1
[15 empty] | D9 | B9/N5 | E9 | B9/Q5 | F9 | B9/T5
[15 empty] | D10 | B10/N5 | E10 | B10/Q5 | F10 | B10/T5 |  |  | Number of AD = Number of B
[15 empty] | D11 | B11/N5 | E11 | B11/Q5 | F11 | B11/T5 |  |  | AD1 | B1/150 (ProBect#1,2,3,4)
[15 empty] | D12 | B12/N5 | E12 | B12/Q5 | F12 | B12/T5 |  |  | AD2 | B2/150 (ProBect#1,2,3,4)
[23 empty] | AD3 | B3/150 (ProBect#1,2,3,4)
[15 empty] | Number of D = Number of B (Swap-Very High risk) |  | Number of E = Number B (SWAP-Very High risk) |  | Number of F = Number B (Swap-Very High Risk) |  |  |  | AD4 | B4/150 (ProBect#1,2,3,4)
[15 empty] | D1 | B1/O9 | E1 | B1/R9 | F1 | B1/U9 |  |  | AD5 | B5/150 (ProBect#1,2,3,4)
[15 empty] | D2 | B2/O9 | E2 | B2/R9 | F2 | B2/U9 |  |  | AD6 | B6/150 (ProBect#1,2,3,4)
[15 empty] | D3 | B3/O9 | E3 | B3/R9 | F3 | B3/U9 |  |  | AD7 | B7/150 (ProBect#1,2,3,4)
[15 empty] | D4 | B4/O5 | E4 | B4/R5 | F4 | B4/U5 |  |  | AD8 | B8/150 (ProBect#1,2,3,4)
[15 empty] | D5 | B5/O5 | E5 | B5/R5 | F5 | B5/U5 |  |  | AD9 | B9/150 (ProBect#1,2,3,4)
[15 empty] | D6 | B6/O5 | E6 | B6/R5 | F6 | B6/U5 |  |  | AD10 | B10/150 (ProBect#1,2,3,4)
[15 empty] | D7 | B7/O5 | E7 | B7/R5 | F7 | B7/U5 |  |  | AD11 | B11/150 (ProBect#1,2,3,4)
[15 empty] | D8 | B8/O5 | E8 | B8/R5 | F8 | B8/U5 |  |  | AD12 | B12/150 (ProBect#1,2,3,4)
[15 empty] | D9 | B9/O5 | E9 | B9/R5 | F9 | B9/U5 |  |  | In case of result Less than 1 consider 1
[15 empty] | D10 | B10/O5 | E10 | B10/R5 | F10 | B10/U5
[15 empty] | D11 | B11/O5 | E11 | B11/R5 | F11 | B11/U5 |  |  | Number of AE = Number of B
[15 empty] | D12 | B12/O5 | E12 | B12/R5 | F12 | B12/U5 |  |  | AE1 | B1/100
[23 empty] | AE2 | B2/100
[23 empty] | AE3 | B3/100
[23 empty] | AE4 | B4/100
[23 empty] | AE5 | B5/100
[23 empty] | AE6 | B6/100
[23 empty] | AE7 | B7/100
[23 empty] | AE8 | B8/100
[23 empty] | AE9 | B9/100
[23 empty] | AE10 | B10/100
[23 empty] | AE11 | B11/100
[23 empty] | AE12 | B12/100
In case of result Less than 1 consider 1, Zero in CW